# My Clinic — Phase 0 kick-off pack

Kick-off working document · Agenda, attendees, pre-reads and the complete open-decision list with owners and due dates. Recommended answers are drafts for the named owner to confirm in writing; nothing here is approved course content.

| Document | MC-KO-01 · Phase 0 kick-off pack + decision sheet |
| --- | --- |
| Revision | v0.1 · 14 October 2026 |
| Proposed kick-off | Monday 2026-10-19 (week 1 of the proposal timeline) |
| Status | Working document — decisions are recorded in the Phase 0 files, not here |
| Sources | 00_program/kickoff-pack.md + 00_program/decision-sheet.md (generated) |
| Companion files | client-review pack (9 Word docs) · decision-sheet.csv · storyboard-review-register.csv · proposal Rev01 |

# Phase 0 kick-off pack — My Clinic induction e-learning

Document MC-KO-01 · v0.2 · 2026-10-19 (v0.1 2026-10-14). Working pack for the Phase 0 kick-off meeting

(proposed Monday 2026-10-19, week 1 of the proposal timeline). It exists so the meeting

closes decisions instead of discovering them: every open item already has an owner role, a

draft recommendation and a due date in the decision sheet.

Nothing in this pack is approved course content; recommended answers are drafts for the named

owner to confirm in writing.

────────────────────────────────────────────────────

## 1. What is ready, in one paragraph

Eight SCORM packages (six client courses), 207 core screens, 95 scored activities, ~62 minutes of

two-voice narration, all at storyboard v0.2 with clean planning lint, a branded visual board per

module, an asset register per module and a client-shareable Word rendering per module. Proposal

Rev01 matches those numbers. What is *not* ready is every fact that My Clinic owns: 102 open

decisions (28 safety/PHI/incident, 3 programme enablers, 71 module content facts), the voice route

(D10), the LMS and SCORM version (D9), brand confirmation (D11), and the module-08 test-environment

captures. Release builds cannot start until the tier-1 and tier-3 rows are closed.

New since v0.1 (2026-10-19): all eight packages exist as compiled, validated v0.1-draft SCORM

packages (open facts shown as ⚠ Draft — pending); the full-size Noor and Dr. Omar artwork is in;

every screen carries the My Clinic brand weave. Because My Clinic runs Oracle Applications Cloud, the

packages are now SCORM 1.2 for Oracle Learning, and an 8-minute Oracle Learning sample package

with a test guide is ready for the LMS team — bring the result of that test to close D9.

## 2. Proposed 90-minute session

| Min | Item | Lead | Outcome before leaving the room |
| --- | --- | --- | --- |
| 0–10 | Programme shape: 6 courses / 8 packages, learning path 03 → 07 → 01 → 02 → 04 → 05 → 06 → 08, Rev01 figures, 9–10 week plan | L2S | Shared picture; no debate on scope |
| 10–25 | Walk one storyboard end to end (module 04, 13 screens): what a v0.2 card contains, the ⚠ PENDING convention, what the Word pack shows | L2S | Reviewers know how to read the pack |
| 25–45 | Tier 1 (28 rows): D1 Code Orange, D2 code sheet + real extensions, D5 personal data, D6 IT video/PHI, D8 24-hour rule, plus the safety, radiation, IPSG, identifier and test-environment rows | Safety Manager, RSO, Nursing Director, DPO, IT | Owner + date confirmed per row; where the draft recommendation is accepted, say so and write it down |
| 45–60 | Tier 3 enablers: D9 LMS + SCORM version (Oracle Learning, SCORM 1.2 — sample test result), D10 voice route (hear the two companion voice briefs), D11 brand confirmation | L&D/IT, course owner, Marketing | Three decisions or a named date inside week 2 |
| 60–80 | Tier 2 by module (71 rows): agree the route, not the answers — who confirms leave tables, ICD-10 edition, rejection-log rebuild, org-chart lines, branch names | Module SMEs | Each module's rows assigned with dates ≤ 2026-10-30 |
| 80–90 | Write-back procedure, tracker import of the register CSV, next checkpoint, pilot window | L2S | Calendar entries; procedure accepted |

## 3. Who should be in the room

| Role | Decisions they own in this meeting |
| --- | --- |
| Safety & Security Manager (SME lead 01/02) | D1, D2, D12; 01 B1–B10; 02 B1–B9 |
| Radiation Safety Officer | 01 B4, B5 |
| Facilities / Engineering + Infection Control / EHS | 01 B6, B7; 02 spill and waste rows |
| HR lead + Communications | 03 B1–B14; D3, D5, D13 |
| Director of Operations + My Care Manager | 04 B1–B7 |
| RCM lead, Coding lead, Payer Relations | 05 B1–B10; 06 B1–B9; D4 |
| Quality Director + Patient Safety / Risk Manager | 07 B1–B11, NEW-01, P01; D7, D8 |
| EHR Applications lead + DPO + IT | 08 B1–B10; D6 |
| L&D / course owner | D9, D10, D14; scope and seat time |
| Marketing | D11 |

## 4. Pre-reads (send with the invite)

Proposal Rev01 (PDF) — numbers and phases.

Storyboard review pack (Word index) and the eight module renderings in ../client-review/.

Decision sheet (Markdown) · tracker CSV — the 102 open rows.

SME / build-detail register CSV — the 52 screen-level authoring questions (import into your tracker).

Asset & template audit — what exists, what is still to be supplied (consented photos, test captures; companion art is done).

Programme status, the project map and the production board.

Oracle Learning sample package + test guide — for the LMS administrator before the D9 item.

## 5. Same-day write-back procedure

Owner writes the decision and its source (policy number, poster, email, screenshot) in the

file named in the decision sheet's “Write back to” column: cross-module-decisions.md for D*,

the module's phase-0-source-lock.md (§2 row + §4 verified-facts register) for B*/NEW*.

Status becomes Closed (YYYY-MM-DD) in that file.

L2S reruns the gate chain (roadmap §standard exit gate): generator/normaliser → lint_planning.py

→ build_scorm_structure.py → export_storyboard_docx.py → build_decision_sheet.py (the closed

row disappears from the open list) → export_kickoff_docx.py → audit_assets.py, which must exit

clean.

If a decision changes a screen (wording, number, branch name), the same PR updates the Phase 2

row and the storyboard card — never the card alone.

## 6. What the room does not decide

Clinical or policy judgement beyond the sources: the plans only carry what the source documents

say, marked ⚠ PENDING until an owner confirms.

LMS procurement and licence cost (D9 records the platform and SCORM version only).

Voice provider contract value (D10 records route, provider and voice ids only).

Anything that would put real patient, staff or claim data into a package: those rows close with

“rebuild with fictional data”, never with “use the source file”.

## 7. After the kick-off

Tier 1 + tier 3 closed → chunks C2–C5 (SME build-detail closure per module pair) and C6–C9

(voices, companion art, brand, 08 captures) start in parallel; Phase 3 media production (C10–C13)

follows per module in build order. See next-phases-roadmap.md.

# Attachment — Phase 0 decision sheet (open rows)

Generated by tools/build_decision_sheet.py on 2026-10-14 from the controlled Phase 0 files, the cross-module decision log, the SCORM structure summary and programme gap G2/G4. Proposed kick-off: 2026-10-19 (proposed). Recommended answers are drafts copied from the plans for the owner to confirm — nothing here is policy until the owner writes it into the file named in “Write back to”.

| Scope | Count |
| --- | --- |
| Open decisions listed | 102 |
| Tier 1 — safety, identifiers, PHI, incident rules (due 2026-10-22 (K+3 wd)) | 28 |
| Tier 3 — programme enablers D9/D10/D11 (due 2026-10-26 (K+5 wd)) | 3 |
| Tier 2 — module content facts (due 2026-10-30 (end of week 2)) | 71 |

How to close a row: the owner writes the decision and its source (policy number, poster, email) in the Phase 0 / decision-log file named in “Write back to”, sets its status to Closed (date), then rerun the standard gate chain (see next-phases-roadmap.md). This sheet is regenerated, never edited by hand.

## Tier 1 — due 2026-10-22 (K+3 wd)

| ID | Module(s) | Decision needed | Recommended answer (draft) | Owner (role) | Due | Write back to | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 01/B1 | 01 FMS | Code Orange threshold (source: p.40 vs H&S 2 p.22) | See program decision D1 | Safety Manager | 2026-10-22 (K+3 wd) | 01_health-and-safety-1/phase-0-source-lock.md row B1 + §4 verified-facts register | Open |
| 01/B2 | 01 FMS | Code names and extension numbers (11 codes + 2 announcements) (source: pp.17–19) | See D2. Need the facility's code poster. | Safety Manager | 2026-10-22 (K+3 wd) | 01_health-and-safety-1/phase-0-source-lock.md row B2 + §4 verified-facts register | Open |
| 01/B4 | 01 FMS | Radiation dose limits and bands (2 mSv / 3 months, 20 mSv / year; 1.25 / 1.25–3.75 / > 3.75 mSv) (source: p.59) | Confirm against current national regulation and facility policy; confirm whether the bands are per quarter | RSO | 2026-10-22 (K+3 wd) | 01_health-and-safety-1/phase-0-source-lock.md row B4 + §4 verified-facts register | Open |
| 01/B5 | 01 FMS | Laser class table wording ("3" vs "3R" vs "3B") (source: p.61) | Confirm current IEC class names used at the facility | RSO | 2026-10-22 (K+3 wd) | 01_health-and-safety-1/phase-0-source-lock.md row B5 + §4 verified-facts register | Open |
| 01/B7 | 01 FMS | Waste segregation bin colours (source: p.41) | The deck says colours vary; get the facility's bin colours so the drag-and-drop matches real bins | Infection Control / EHS | 2026-10-22 (K+3 wd) | 01_health-and-safety-1/phase-0-source-lock.md row B7 + §4 verified-facts register | Open |
| 02/B1 | 02 Safety Lab | Code Orange threshold ("< 1 L minor" vs "> 500 mL Code Orange") (source: p.22) | Program D1 | Safety Manager | 2026-10-22 (K+3 wd) | 02_health-and-safety-2/phase-0-source-lock.md row B1 + §4 verified-facts register | Open |
| 02/B2 | 02 Safety Lab | Extension "5555" placeholder on the bilingual code table (source: p.5) | Program D2; also Code Silver wording | Safety Manager + Switchboard | 2026-10-22 (K+3 wd) | 02_health-and-safety-2/phase-0-source-lock.md row B2 + §4 verified-facts register | Open |
| 02/B4 | 02 Safety Lab | Spill-kit procedure page is blank (source: p.29) | Write the procedure. Proposed: PPE per SDS → isolate & warn → contain the edges → absorb / neutralise → bag, seal, label as hazardous waste → clean area → report to supervisor & Safety Services → restock the kit | EHS | 2026-10-22 (K+3 wd) | 02_health-and-safety-2/phase-0-source-lock.md row B4 + §4 verified-facts register | Open |
| 02/B9 | 02 Safety Lab | Empty contact boxes on the closing page (source: p.31) | Contact role + extension for the final screen | Safety Manager | 2026-10-22 (K+3 wd) | 02_health-and-safety-2/phase-0-source-lock.md row B9 + §4 verified-facts register | Open |
| 03/B13 | 03 Welcome On Board | SCFHS rule: suspension with 30 days left before licence expiry (source: 49) | Confirm | HR | 2026-10-22 (K+3 wd) | 03_hr-employee-induction/phase-0-source-lock.md row B13 + §4 verified-facts register | Open |
| 03/B14 | 03 Welcome On Board | Ethics: "incident report within 24 hours" for ethical dilemmas (source: 21) | Keep consistent with module 07 (program D8) | Compliance | 2026-10-22 (K+3 wd) | 03_hr-employee-induction/phase-0-source-lock.md row B14 + §4 verified-facts register | Open |
| 03/B6 | 03 Welcome On Board | Personal data: leader photos and names, HR help-desk emails and named contacts, presenter name (source: 2, 12–13, 30) | Program D5. Recommended: leaders with consent; help desk as role mailboxes, no personal names | DPO + HR | 2026-10-22 (K+3 wd) | 03_hr-employee-induction/phase-0-source-lock.md row B6 + §4 verified-facts register | Open |
| 06/B8 | 06 RCM Part B | Rejection log (slide 6): claim numbers, provider names, dates (source: 6) | Do not use the image. Rebuild 8–10 rows with invented claim ids and only the rejection comment + diagnosis; DPO approves | RCM lead + DPO | 2026-10-22 (K+3 wd) | 06_rcm-ebp-benefits-and-rejections/phase-0-source-lock.md row B8 + §4 verified-facts register | Open |
| 07/B1 | 07 Clinical Governance | Transcript accuracy — the narration was machine-transcribed with heavy errors (source: whole video; CHUNKS_10s.md) | One person listens to the full video and corrects the cleaned narration in the source Markdown §3. No sentence is quoted until this is done | L&D + Quality | 2026-10-22 (K+3 wd) | 07_quality-safety-and-risk/phase-0-source-lock.md row B1 + §4 verified-facts register | Open |
| 07/B2 | 07 Clinical Governance | Video licence and NotebookLM watermark (source: frames 00:40–05:20) | Program D7 (recommended: do not ship the video) | Quality Director | 2026-10-22 (K+3 wd) | 07_quality-safety-and-risk/phase-0-source-lock.md row B2 + §4 verified-facts register | Open |
| 07/B3 | 07 Clinical Governance | IPSG wording and numbering (Goal 1 identification … Goal 6 falls) (source: 02:40–04:10) | Match the facility's IPSG policy (JCI/CBAHI wording) | Patient Safety Officer | 2026-10-22 (K+3 wd) | 07_quality-safety-and-risk/phase-0-source-lock.md row B3 + §4 verified-facts register | Open |
| 07/B4 | 07 Clinical Governance | Identifier rule: full name + MRN; age and room never; add DOB or ID when names match (source: 03:20 frame) | Confirm the two identifiers and the "same name" rule | Nursing Director | 2026-10-22 (K+3 wd) | 07_quality-safety-and-risk/phase-0-source-lock.md row B4 + §4 verified-facts register | Open |
| 07/B5 | 07 Clinical Governance | Fall-risk identifier: bright-yellow band (source: 04:10 (narration only)) | Confirm against the falls policy | Nursing Director | 2026-10-22 (K+3 wd) | 07_quality-safety-and-risk/phase-0-source-lock.md row B5 + §4 verified-facts register | Open |
| 07/B8 | 07 Clinical Governance | Incident definitions: critical / sentinel event vs adverse event vs near miss; examples (source: 06:25–07:20) | Confirm terms used in the incident policy ("critical incident" vs "sentinel event") | Risk Manager | 2026-10-22 (K+3 wd) | 07_quality-safety-and-risk/phase-0-source-lock.md row B8 + §4 verified-facts register | Open |
| 07/B9 | 07 Clinical Governance | 24-hour reporting rule; channel (online system / email); severity 1–2 escalated within department (source: 07:30–08:40) | Program D8; confirm channel name and severity levels | Risk Manager | 2026-10-22 (K+3 wd) | 07_quality-safety-and-risk/phase-0-source-lock.md row B9 + §4 verified-facts register | Open |
| 08/B1 | 08 EHR | Patient identifiers in IT.mp4 (5:10–6:10 full record; 7:10–7:20 phone; 8:30 ID) (source: video) | Program D6: the video and its frames are not used. Decide separately whether to remove the file from Git history and Drive sharing | IT + DPO | 2026-10-22 (K+3 wd) | 08_it-ehr-consultation/phase-0-source-lock.md row B1 + §4 verified-facts register | Open |
| 08/B2 | 08 EHR | Test environment + test patient ("Test Simplified Template Launch" or new) for all new screenshots (source: —) | Provide test login, test patient with fictional demographics, and a capture session (1920×1080, browser zoom 125% for legibility) | EHR lead | 2026-10-22 (K+3 wd) | 08_it-ehr-consultation/phase-0-source-lock.md row B2 + §4 verified-facts register | Open |
| 08/B4 | 08 EHR | Mandatory fields before completing a consultation (source: 00:30, 07:30) | Exact list (chief complaint, duration, HPI, past history incl. allergies and medications, examination, plan of care, diagnosis, patient & family education?) | EHR lead | 2026-10-22 (K+3 wd) | 08_it-ehr-consultation/phase-0-source-lock.md row B4 + §4 verified-facts register | Open |
| D1 | 01, 02 | Code Orange spill threshold [1] | Recommended: *spill ≥ 500 mL, or any highly toxic/reactive/explosive substance → Code Orange; otherwise call the cleaning supervisor.* Removes the "< 1 L minor spill" wording. | Safety & Security Manager | 2026-10-22 (K+3 wd) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |
| D2 | 01, 02, 07 | Emergency code sheet — one naming set (e.g. Code Silver "violent situation involving a weapon" vs "active shooter with weapon"; RRT included or not) and the real extension numbers (decks show "5555") [2] | Use the facility's current MOH code poster as the single source. Code Blue 2222 is national. | Safety & Security Manager + Switchboard | 2026-10-22 (K+3 wd) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |
| D5 | 03, 04, 06 | Personal data policy for the course: staff names, photos, emails, claim numbers [17] | Recommended: roles on screen, names in a linked live directory; leadership photos only with consent; claim log fully anonymised and rebuilt. | HR + Data Protection Officer | 2026-10-22 (K+3 wd) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |
| D6 | 08 | IT video with patient identifiers [13, 18] | Do not use IT.mp4 in any package. Re-capture all screens on a test patient. Separately decide whether to purge the file from Git history. | IT + Data Protection Officer | 2026-10-22 (K+3 wd) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |
| D8 | 03, 07 | Incident reporting window — 24 hours (Quality video and HR ethics slide) | Confirm against the incident-reporting policy; keep the same wording in both modules. | Quality / Risk Manager | 2026-10-22 (K+3 wd) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |

## Tier 3 — due 2026-10-26 (K+5 wd)

| ID | Module(s) | Decision needed | Recommended answer (draft) | Owner (role) | Due | Write back to | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D10 | all | Voice route and provider | External English TTS for release 1 (see narration-and-lexicon.md). | Course owner | 2026-10-26 (K+5 wd) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |
| D11 | all | Brand kit | Brand taken from My Clinic's own decks (brand/brand-identity.md): navy #003867, value colours, Montserrat, logo files. Marketing to confirm or send the official guide. | Marketing | 2026-10-26 (K+5 wd) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open — draft in use |
| D9 | all | LMS and SCORM version | My Clinic uses Oracle Applications Cloud (HR source: Oracle self-service), so the LMS is expected to be Oracle Learning. Recommended: SCORM 1.2 for all eight packages (Oracle documents 1.2 and 2004 Ed. 2–3; compiler emits 2004 4th Ed.). Confirm with the sample package test (00_sample-oracle-pilot/). | L&D / IT | 2026-10-26 (K+5 wd) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open — recommendation applied to builds, awaiting Oracle sample-test result |

## Tier 2 — due 2026-10-30 (end of week 2)

| ID | Module(s) | Decision needed | Recommended answer (draft) | Owner (role) | Due | Write back to | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 01/B10 | 01 FMS | Completion actions (acknowledgement form, evacuation route, numbers) (source: p.65) | How the acknowledgement is captured (see D14) | L&D | 2026-10-30 (end of week 2) | 01_health-and-safety-1/phase-0-source-lock.md row B10 + §4 verified-facts register | Open |
| 01/B3 | 01 FMS | [Facility Name], [Month Year] placeholders (source: p.1) | Facility name(s) to show; or "My Clinic" generic | L&D | 2026-10-30 (end of week 2) | 01_health-and-safety-1/phase-0-source-lock.md row B3 + §4 verified-facts register | Open |
| 01/B6 | 01 FMS | Emergency (red) socket colour and generator timing ("within seconds") (source: p.46) | Confirm for each branch | Facilities | 2026-10-30 (end of week 2) | 01_health-and-safety-1/phase-0-source-lock.md row B6 + §4 verified-facts register | Open |
| 01/B8 | 01 FMS | Department Safety Liaison list (source: p.14) | Not needed on screen; learners are told to ask their supervisor. Confirm the wording. | Safety Manager | 2026-10-30 (end of week 2) | 01_health-and-safety-1/phase-0-source-lock.md row B8 + §4 verified-facts register | Open |
| 01/B9 | 01 FMS | Accreditation references (CBAHI chapter name, ISO 45001 rights) (source: pp.3, 15) | Confirm current CBAHI edition and wording | Quality / Accreditation | 2026-10-30 (end of week 2) | 01_health-and-safety-1/phase-0-source-lock.md row B9 + §4 verified-facts register | Open |
| 01/G4 | 01 FMS | Thin objective evidence: 4 objective(s) assessed by one scored screen (hs1-o1, hs1-o6, hs1-o7, hs1-o10) | hs1-o1: accept single-evidence at SME sign-off, or add a short check; hs1-o6: add one second short scored check (Phase 2 change, SME approves); hs1-o7: add one second short scored check (Phase 2 change, SME approves); hs1-o10: capstone — accept the single case at sign-off | SME lead + L&D | 2026-10-30 (end of week 2) | 01_health-and-safety-1/phase-1-action-map.md evidence map + 01_health-and-safety-1/phase-2-storyboard.md if a check is added | Open |
| 02/B3 | 02 Safety Lab | "First Clinic" template / other author in PDF metadata (source: metadata) | Program D12; until closed, use no H&S 2 images | Safety Manager | 2026-10-30 (end of week 2) | 02_health-and-safety-2/phase-0-source-lock.md row B3 + §4 verified-facts register | Open |
| 02/B5 | 02 Safety Lab | Chemical register example (Radiology, Sep 2025): product names, volumes, NFPA ratings small and partly unreadable (source: p.25) | Get the current register (any department) as a spreadsheet; anonymise supplier details; confirm NFPA ratings per SDS | EHS | 2026-10-30 (end of week 2) | 02_health-and-safety-2/phase-0-source-lock.md row B5 + §4 verified-facts register | Open |
| 02/B6 | 02 Safety Lab | Hazard-spotting picture has no answer key (source: p.4) | Approve the authored answer key (Phase 2, hs2-010) and a new own illustration (do not reuse the cartoon until B3 is closed) | Safety Manager | 2026-10-30 (end of week 2) | 02_health-and-safety-2/phase-0-source-lock.md row B6 + §4 verified-facts register | Open |
| 02/B7 | 02 Safety Lab | Facility evacuation floor plan (the sample map is generic) (source: p.12) | Use a generic own floor plan in the course + a line telling learners to find their unit's plan. Real floor plans are not put in the package (security). | Safety Manager | 2026-10-30 (end of week 2) | 02_health-and-safety-2/phase-0-source-lock.md row B7 + §4 verified-facts register | Open |
| 02/B8 | 02 Safety Lab | Assembly point signs (inside / outside) (source: p.14) | Confirm assembly point names per branch, or keep generic | Safety Manager | 2026-10-30 (end of week 2) | 02_health-and-safety-2/phase-0-source-lock.md row B8 + §4 verified-facts register | Open |
| 02/G4 | 02 Safety Lab | Thin objective evidence: 3 objective(s) assessed by one scored screen (hs2-o2, hs2-o4, hs2-o7) | hs2-o2: accept single-evidence at SME sign-off, or add a short check; hs2-o4: accept single-evidence at SME sign-off, or add a short check; hs2-o7: accept single-evidence at SME sign-off, or add a short check | SME lead + L&D | 2026-10-30 (end of week 2) | 02_health-and-safety-2/phase-1-action-map.md evidence map + 02_health-and-safety-2/phase-2-storyboard.md if a check is added | Open |
| 03/B1 | 03 Welcome On Board | Sick-leave pay: "days 31–90: 25% deducted" (= 75% pay?) (source: 35) | Confirm the current policy text and the pay % for each band | HR | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B1 + §4 verified-facts register | Open |
| 03/B10 | 03 Welcome On Board | Scientific leave days by profession and "academic exams" wording copied from exam leave (source: 39–40) | Confirm; the slide 40 sentence about academic exams looks copied from slide 38 | HR | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B10 + §4 verified-facts register | Open |
| 03/B11 | 03 Welcome On Board | Hajj leave (2 years' service, 10–15 days incl. Eid) (source: 41) | Confirm | HR | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B11 + §4 verified-facts register | Open |
| 03/B12 | 03 Welcome On Board | GOSI rates (9.75% employee, 11.75% company, 21.5% total; Saudi only) (source: 45–46) | Confirm against current GOSI rates for new joiners | HR / Payroll | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B12 + §4 verified-facts register | Open |
| 03/B2 | 03 Welcome On Board | Compassionate leave: "130 calendar days" (Muslim female employee, death of husband) and "15 days" (non-Muslim) (source: 42) | Confirm the exact wording and the legal basis | HR | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B2 + §4 verified-facts register | Open |
| 03/B3 | 03 Welcome On Board | Overtime "depends on grade" but one formula is given (source: 48) | Which grades are eligible; is the formula the same for all? | HR | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B3 + §4 verified-facts register | Open |
| 03/B4 | 03 Welcome On Board | ID-card loss penalty 100 SAR (source: 55) | Confirm | HR | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B4 + §4 verified-facts register | Open |
| 03/B5 | 03 Welcome On Board | Branch names: J3 Al Andalus vs Al Tahlia; J4 Abhor vs Obhur; PR1 vs PRC (source: 14–16) | Program D3 | HR + Comms | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B5 + §4 verified-facts register | Open |
| 03/B7 | 03 Welcome On Board | Awards and accreditation claims (CBAHI scores 98.67 / 100, JCI news clip) (source: 17–18) | Confirm the exact body, year and wording; JCI claim must be verifiable | Comms + Quality | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B7 + §4 verified-facts register | Open |
| 03/B8 | 03 Welcome On Board | Oracle screenshots must come from a test account (source: 50–52) | Provide a test login or approved screenshots with no real employee data | HRIS | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B8 + §4 verified-facts register | Open |
| 03/B9 | 03 Welcome On Board | Annual leave carry-over (5 days, end of March; consulting-room physicians end of June) and entitlement by grade (source: 33–34) | Confirm for the current year | HR | 2026-10-30 (end of week 2) | 03_hr-employee-induction/phase-0-source-lock.md row B9 + §4 verified-facts register | Open |
| 04/B1 | 04 Who Does What | Reporting lines for the Operations chart (source: 3) | A role-only chart (boxes and lines) approved by the Director | Director of Operations | 2026-10-30 (end of week 2) | 04_operations-and-my-care/phase-0-source-lock.md row B1 + §4 verified-facts register | Open |
| 04/B2 | 04 Who Does What | Reporting lines for the My Care chart (source: 6) | Same, approved by the My Care Manager | My Care Manager | 2026-10-30 (end of week 2) | 04_operations-and-my-care/phase-0-source-lock.md row B2 + §4 verified-facts register | Open |
| 04/B3 | 04 Who Does What | Abbreviations: FM, DMP, CHP, PR1, VIP team, Check Up Unit, In Patient (source: 3, 5) | Full names and one-line definitions | Operations | 2026-10-30 (end of week 2) | 04_operations-and-my-care/phase-0-source-lock.md row B3 + §4 verified-facts register | Open |
| 04/B4 | 04 Who Does What | Which headcount (PXOs/FMs/Coords) belongs to which unit (source: 3, 6) | Not needed on screen if the course stays role-based. Confirm we drop headcounts | Director of Operations | 2026-10-30 (end of week 2) | 04_operations-and-my-care/phase-0-source-lock.md row B4 + §4 verified-facts register | Open |
| 04/B5 | 04 Who Does What | PR1 vs PRC; J1–J4 names (source: 3) | Program D3 | HR + Operations | 2026-10-30 (end of week 2) | 04_operations-and-my-care/phase-0-source-lock.md row B5 + §4 verified-facts register | Open |
| 04/B6 | 04 Who Does What | Names on screen (source: 3, 6) | Program D5. Recommended: no names; link to the live directory | HR + DPO | 2026-10-30 (end of week 2) | 04_operations-and-my-care/phase-0-source-lock.md row B6 + §4 verified-facts register | Open |
| 04/B7 | 04 Who Does What | Escalation routes for the scenario (who handles on-spot complaints, insurance follow-ups, priority bookings, telemedicine coordination) (source: 2, 5) | Confirm the right team for each of the 8 scenario requests in Phase 2 | PX Sr. Manager + My Care Manager | 2026-10-30 (end of week 2) | 04_operations-and-my-care/phase-0-source-lock.md row B7 + §4 verified-facts register | Open |
| 04/G4 | 04 Who Does What | Thin objective evidence: 2 objective(s) assessed by one scored screen (ops-o1, ops-o3) | ops-o1: accept single-evidence at SME sign-off, or add a short check; ops-o3: accept single-evidence at SME sign-off, or add a short check | SME lead + L&D | 2026-10-30 (end of week 2) | 04_operations-and-my-care/phase-1-action-map.md evidence map + 04_operations-and-my-care/phase-2-storyboard.md if a check is added | Open |
| 05/B1 | 05 RCM Part A | Regulator name CCHI vs CHI (source: Objectives; Updates) | Program D4 | RCM lead | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-0-source-lock.md row B1 + §4 verified-facts register | Open |
| 05/B10 | 05 RCM Part A | Clinical examples (IV fluids for dehydration; multi-joint pain with anti-DNA/anti-Ro/anti-La) (source: Medical necessity; Defensive medicine) | Medical Director confirms they are appropriate teaching examples | Medical Director | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-0-source-lock.md row B10 + §4 verified-facts register | Open |
| 05/B2 | 05 RCM Part A | Vitamin D repeat interval ("not less than 118") (source: Avoid excessive ordering) | The payer-approved minimum interval | RCM lead + payer relations | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-0-source-lock.md row B2 + §4 verified-facts register | Open |
| 05/B3 | 05 RCM Part A | HbA1c repeat interval ("before 89 day") (source: Avoid excessive ordering) | The payer-approved minimum interval (≈ 90 days?) | RCM lead | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-0-source-lock.md row B3 + §4 verified-facts register | Open |
| 05/B4 | 05 RCM Part A | ICD-10 edition used for claims in KSA (ICD-10-AM?) and the exact codes for each example: R50, R05, R11, K52, J03, I10, E66, L70, L66, L21, N46, N97, general check-up (Z00?) (source: ICD-10 sections) | Coder confirms code + title in the edition used. Note: *vomiting → gastroenteritis* may code as A09 (infectious) or K52 (non-infective); the example must use the right one | Coding lead | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-0-source-lock.md row B4 + §4 verified-facts register | Open |
| 05/B5 | 05 RCM Part A | Obesity: uncovered, but covered with BMI > 40 and surgical referral (source: Avoid uncovered codes) | Confirm against the current table of benefits | Payer relations | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-0-source-lock.md row B5 + §4 verified-facts register | Open |
| 05/B6 | 05 RCM Part A | PCOS hormonal assessment rejected vs menopause hormonal assessment and HRT approved (source: Amended benefits) | Confirm (links to module 06 women's-health benefit) | Payer relations | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-0-source-lock.md row B6 + §4 verified-facts register | Open |
| 05/B7 | 05 RCM Part A | Mental-health sub-limit 50,000 SAR + pre-authorisation (source: Added benefits) | Covered in module 06; here only mentioned. Confirm or drop | Payer relations | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-0-source-lock.md row B7 + §4 verified-facts register | Open |
| 05/B8 | 05 RCM Part A | "Combined supplements are treated as defensive medicine" (source: Avoid defensive medicine) | Confirm wording and whether it's a payer rule or internal guidance | RCM lead | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-0-source-lock.md row B8 + §4 verified-facts register | Open |
| 05/B9 | 05 RCM Part A | Pre-authorisation workflow ("submit diagnosis with the request to get pre-authorisation at the first attempt") (source: Objectives) | Confirm the steps in the clinic's EHR (links to module 08) | RCM lead | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-0-source-lock.md row B9 + §4 verified-facts register | Open |
| 05/G4 | 05 RCM Part A | Thin objective evidence: 1 objective(s) assessed by one scored screen (rcma-o5) | rcma-o5: capstone — accept the single case at sign-off | SME lead + L&D | 2026-10-30 (end of week 2) | 05_rcm-documentation-and-coding/phase-1-action-map.md evidence map + 05_rcm-documentation-and-coding/phase-2-storyboard.md if a check is added | Open |
| 06/B1 | 06 RCM Part B | Deck date "August 30, 2023" vs file name "2026" (source: 1–2) | Which EBP version is current; course cover shows the policy effective date, not the talk date | RCM lead | 2026-10-30 (end of week 2) | 06_rcm-ebp-benefits-and-rejections/phase-0-source-lock.md row B1 + §4 verified-facts register | Open |
| 06/B2 | 06 RCM Part B | Regulator name CCHI vs CHI (source: 3–4, 8–12) | Program D4 | RCM lead | 2026-10-30 (end of week 2) | 06_rcm-ebp-benefits-and-rejections/phase-0-source-lock.md row B2 + §4 verified-facts register | Open |
| 06/B3 | 06 RCM Part B | Every benefit on slides 8–12 checked against the official EBP document (text is small and approximate) (source: 8–12) | Line-by-line check; provide the official document reference | Payer relations | 2026-10-30 (end of week 2) | 06_rcm-ebp-benefits-and-rejections/phase-0-source-lock.md row B3 + §4 verified-facts register | Open |
| 06/B4 | 06 RCM Part B | Counts: "18 added / 10 amended" vs 10 and 8 headline items (source: 8) | Use the headline items only and drop the counts, or confirm the full lists | Payer relations | 2026-10-30 (end of week 2) | 06_rcm-ebp-benefits-and-rejections/phase-0-source-lock.md row B4 + §4 verified-facts register | Open |
| 06/B5 | 06 RCM Part B | Limits: mental health 50,000 SAR per policy period; kidney transplant 250,000 SAR (source: 10, 12) | Confirm | Payer relations | 2026-10-30 (end of week 2) | 06_rcm-ebp-benefits-and-rejections/phase-0-source-lock.md row B5 + §4 verified-facts register | Open |
| 06/B6 | 06 RCM Part B | Optical cover wording ("life-threatening congenital illness for beneficiaries up to 14 years") (source: 8) | The slide wording looks garbled; confirm the actual benefit | Payer relations | 2026-10-30 (end of week 2) | 06_rcm-ebp-benefits-and-rejections/phase-0-source-lock.md row B6 + §4 verified-facts register | Open |
| 06/B7 | 06 RCM Part B | Behavioural/dietary consultation criteria ("BMI > 30 or ≥ 2 risk factors") (source: 9) | Confirm exact criteria | Payer relations | 2026-10-30 (end of week 2) | 06_rcm-ebp-benefits-and-rejections/phase-0-source-lock.md row B7 + §4 verified-facts register | Open |
| 06/B9 | 06 RCM Part B | Rejection categories (source: 6) | Agree the category set used in the sort (proposed: Documentation · Coding · Policy / pre-authorisation · Timing / follow-up period · Billing process) | Coding lead | 2026-10-30 (end of week 2) | 06_rcm-ebp-benefits-and-rejections/phase-0-source-lock.md row B9 + §4 verified-facts register | Open |
| 06/G4 | 06 RCM Part B | Thin objective evidence: 1 objective(s) assessed by one scored screen (rcmb-o1) | rcmb-o1: accept single-evidence at SME sign-off, or add a short check | SME lead + L&D | 2026-10-30 (end of week 2) | 06_rcm-ebp-benefits-and-rejections/phase-1-action-map.md evidence map + 06_rcm-ebp-benefits-and-rejections/phase-2-storyboard.md if a check is added | Open |
| 07/B10 | 07 Clinical Governance | Hand hygiene five moments (WHO) wording (source: 04:10) | Confirm the facility poster wording | Infection Control | 2026-10-30 (end of week 2) | 07_quality-safety-and-risk/phase-0-source-lock.md row B10 + §4 verified-facts register | Open |
| 07/B11 | 07 Clinical Governance | FOCUS-PDCA step names (Find · Organise · Clarify · Understand · Select / Plan · Do · Check · Act) (source: 02:00 frame) | Confirm | Quality Director | 2026-10-30 (end of week 2) | 07_quality-safety-and-risk/phase-0-source-lock.md row B11 + §4 verified-facts register | Open |
| 07/B6 | 07 Clinical Governance | Risk matrix: colour bands and score thresholds (1–25) (source: 05:20 frame (legend small)) | Provide the corporate matrix with band names and ranges | Risk Manager | 2026-10-30 (end of week 2) | 07_quality-safety-and-risk/phase-0-source-lock.md row B6 + §4 verified-facts register | Open |
| 07/B7 | 07 Clinical Governance | Risk responses: reduce/mitigate · transfer · accept (executive approval) · avoid (source: 05:50–06:25) | Confirm the four terms used in the risk policy | Risk Manager | 2026-10-30 (end of week 2) | 07_quality-safety-and-risk/phase-0-source-lock.md row B7 + §4 verified-facts register | Open |
| 07/G4 | 07 Clinical Governance | Thin objective evidence: 1 objective(s) assessed by one scored screen (qsr-o5) | qsr-o5: add one second short scored check (Phase 2 change, SME approves) | SME lead + L&D | 2026-10-30 (end of week 2) | 07_quality-safety-and-risk/phase-1-action-map.md evidence map + 07_quality-safety-and-risk/phase-2-storyboard.md if a check is added | Open |
| 07/P01 | 07 Clinical Governance | Companion placement on qsr-002: Noor sits beside the opening poll, while companions.md §5 keeps companions off question screens. The poll is unscored. | Allow the companion beside unscored polls/reflections (amend companions.md §5 wording), or move Noor to the reflection that follows. | Quality Director + L&D | 2026-10-30 (end of week 2) | 00_program/characters/companions.md §5 + 07_…/phase-2-storyboard.md companion table | Open |
| 08/B10 | 08 EHR | Sick-leave panel (printing disabled) (source: 8:20–8:38) | In scope or not? Recommended: out of scope (separate job aid) | EHR lead | 2026-10-30 (end of week 2) | 08_it-ehr-consultation/phase-0-source-lock.md row B10 + §4 verified-facts register | Open |
| 08/B3 | 08 EHR | EHR product name and version (source: —) | Name it or call it "the clinic EHR"; record the version so screenshots can be refreshed | EHR lead | 2026-10-30 (end of week 2) | 08_it-ehr-consultation/phase-0-source-lock.md row B3 + §4 verified-facts register | Open |
| 08/B5 | 08 EHR | Button and screen names (Today's consultation, Add Diagnosis, Order History, Form Wizard, Consultation Summary, Download and Print, Send SMS, Referral) (source: whole video) | Confirm on the current build | EHR lead | 2026-10-30 (end of week 2) | 08_it-ehr-consultation/phase-0-source-lock.md row B5 + §4 verified-facts register | Open |
| 08/B6 | 08 EHR | Medication and lab examples (lornoxicam, diclofenac, Fevadol non-formulary, Augmentin; CBC, TSH, ECG; vitamin D, "hair package") (source: 1:40–4:50) | Choose 2–3 neutral examples approved by Pharmacy; confirm which item needs non-formulary approval | Pharmacy + Medical Director | 2026-10-30 (end of week 2) | 08_it-ehr-consultation/phase-0-source-lock.md row B6 + §4 verified-facts register | Open |
| 08/B7 | 08 EHR | Clinical disclaimer (source: —) | Wording: "Clinical examples show how to use the system. They are not treatment guidance." | Medical Director | 2026-10-30 (end of week 2) | 08_it-ehr-consultation/phase-0-source-lock.md row B7 + §4 verified-facts register | Open |
| 08/B8 | 08 EHR | SMS education: department list and ICD-10 linked leaflets (source: 7:00) | Confirm the feature exists in the current build and an E11 leaflet is available in test | EHR lead | 2026-10-30 (end of week 2) | 08_it-ehr-consultation/phase-0-source-lock.md row B8 + §4 verified-facts register | Open |
| 08/B9 | 08 EHR | Referral timing options (next available, within a week, two weeks, a month) and internal vs external (source: 7:40–8:20) | Confirm | EHR lead | 2026-10-30 (end of week 2) | 08_it-ehr-consultation/phase-0-source-lock.md row B9 + §4 verified-facts register | Open |
| 08/G4 | 08 EHR | Thin objective evidence: 2 objective(s) assessed by one scored screen (ehr-o2, ehr-o5) | ehr-o2: add one second short scored check (Phase 2 change, SME approves); ehr-o5: accept single-evidence at SME sign-off, or add a short check | SME lead + L&D | 2026-10-30 (end of week 2) | 08_it-ehr-consultation/phase-1-action-map.md evidence map + 08_it-ehr-consultation/phase-2-storyboard.md if a check is added | Open |
| D12 | 02 | Template origin of H&S 2 ("First Clinic" metadata) [15] | Do not reuse H&S 2 template art until confirmed. | Safety & Security Manager | 2026-10-30 (end of week 2) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |
| D13 | 03, program | Clinical Risk and Infection Control sessions (on the HR agenda but no source) [5] | Out of scope for these eight packages. Flag as a gap in the induction curriculum. | L&D | 2026-10-30 (end of week 2) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |
| D14 | 01, 03 | Completion record / acknowledgement form (H&S 1 page 65 asks staff to sign) | Use an LMS attestation step after the SCORM package, or a final poll screen + LMS e-signature. | L&D | 2026-10-30 (end of week 2) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |
| D3 | 03, 04 | Branch names and codes: J3 Al Andalus vs Al Tahlia; J4 Abhor vs Obhur; PR1 vs PRC [6] | Use the names on the current branch signage / official website. | HR + Operations | 2026-10-30 (end of week 2) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |
| D4 | 05, 06 | Regulator name: CCHI vs CHI (Council of Health Insurance) [7] | Use the regulator's current official English name and acronym throughout. | RCM lead (Dr Wafaa Elshayeb or successor) | 2026-10-30 (end of week 2) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |
| D7 | 07 | Quality video licence and watermark [12, 16] | Recommended: rebuild natively; do not ship the NotebookLM video. Optional: a new short intro video made in-house. | Quality Director | 2026-10-30 (end of week 2) | 00_program/cross-module-decisions.md (Decision column) → the Phase 0 tables and storyboard cards of the modules listed | Open |